## Bugs&Features(C++ version)
Section	Bug	What	Who	To be done
Booking system	TimePicker	Devided by zero problem		Tomas
Layout	resize	Tables that are resized are not properly resizing		Tomas
Layout	Rotate Table	Rotation into the opposite direction, when x<starting x point		Tomas
General	Loading XML file	All nodes as added as child	Tomas / Gregor

	Feature
Layout		Right mouse button menus for nodes in the treeview
General		Save to XML file	Tomas / Gregor	Tomas

Booking system		Ok Button (Store to database)
		Cancel button
		Time pickers – look for conflicting dates and times
		Tables – Dialog
		Name – Dialog
		Change into table
Menues

## Team
Who				Assigned to
Tomas	Poland	+1 UTC		Backend
Shareef	Agypt	+2UTC	Prefers evenings (3pm)
Adnan	?	?
Raymond	Malaisia	+8h	Suggestion 2pm UTC	Backend
Eluid Rojas	Maxico	-7h		Android
Bernard Pacho	Brazil	-3h		Backend

## Server
Field	What	Who
General	loading XML files and displaying them in Java SWT tree view	Tomas

Socket programming	Derby DB
	Create a TCP socket server	Shareef
	Define the socket inteferface	Gregor/Shareef

## Meetings
05/02/21	Consensuzs	Open questions	Who
	Use the old swing and Eclipse		Shareef/Tomas/Gregor

	Next meeting is 9th of Feb. 2021 4pm UTC
		Shall we use XML or databse (JSON or XML)
	Next meeting is 16th of Feb. 2021 4pm UTC

	Next meeting is 23th of Feb. 2021 4pm UTC

	March 2nd 4pm UTC	/ Gopinath
		Mahesh Parmar	is looking into the documentation
		Raymond
		Bernard Pacho meeting a day later
	Next team call is at 3pm UTC Tuesday

	Next meeting March 9th 3pm UTC

## Bugs&Features(Java)
Time		Section	Bug	Feature	Details	Who	To be done
	menu		generate uuid, when reading menu		Tomas
	DrillDownMenu		Link the button creations in drill down menu to treeview		Tomas
			Right mouse button menu for editing tree items in tree view	(Delete, Add Nodes, Set Attribute, Set Name, Set price)	Tomas
		Implement the Notbook panel view			Tomas
	DrillDownMenu		Right mouse button menu for editing buttons		Tomas
	DrillDownMenu		Link properties of buttons and drilldown menu with the node view		Tomas
			Names instead of xml tag names should be displayed in the GUI		Tomas
			UUID auto generation		Tomas
			children for width and height in the treeview according to the given example		Tomas
			new drill down menues in the existing drill down menu (change load)		Tomas
			change uuids to long values		Tomas
			Integrate right mouse button functionality for translating Drill Down Menu Buttons	Add x,y position nodes to buttons (now you have width, height, x,y)	Tomas
			when reading the tree the uuids need to be read and stored in a mashmap		Tomas

			Reports (layout for the tables and the document template)		Raymond
			Coding Guidelines		Gregor

30.03.2021		Drill down menu	right mouse button menu for selecting active drill down menu		Tomas
30.03.2021		Drill down menu	Button of the drill down menu should be translatable		Tomas
30.03.2021		Drill down menu	Right mouse button menu for targeting menu nodes		Tomas
30.03.2021		Drill down menu	Deletion of button does not work		Tomas
30.03.2021		Drill down menu	Fix layout with Java (Jumps around etc.)		Tomas